## Sheet1
WBS Item Number | WBS Item Name | Predecessors | Successors | Logical Relationships | Lead and Lags | Resource Requirements | Duration | Start Date | End Date | Assumptions
1.1.1 | Project Charter
1.1.1.1 | Write project charter |  | 1.1.2.1 |  |  | 2 devs | 1 | 2020-10-02 | 2020-10-02
1.1.2 | Project Management Plan | [5 empty] | 1
1.1.2.1 | Write project management plan | 1.1.2.1 |  |  |  | 2 devs | 2 | 2020-10-07 | 2020-10-08
1.1.3 | Assumption Log | [5 empty] | 1
1.1.3.1 | Create assumption log |  |  |  |  | 2 devs | 1 | 2020-10-08 | 2020-10-08
1.1.4 | Business Case | [5 empty] | 1
1.1.4.1 | Develop business case |  |  |  |  | 2 devs | 2 | 2020-10-05 | 2020-10-06
1.1.4.2 | Create weighted scoring model |  |  |  |  | 2 devs | 1 | 2020-10-06 | 2020-10-06
1.1.4.3 | Create payback period chart |  |  |  |  | 2 devs | 1 | 2020-10-06 | 2020-10-06
1.2.1 | Scope Management Plan | [5 empty] | 1
1.2.1.1 | Write scope management plan |  | 1.2.1.2 |  |  | 2 devs | 1 | 2020-10-09 | 2020-10-09
1.2.2 | Scope Statement | [5 empty] | 1
1.2.2.1 | Write scope statement | 1.2.1.1 |  |  |  | 2 devs | 1 | 2020-10-12 | 2020-10-12
1.2.3 | Requirements Management Plan | [5 empty] | 1
1.2.3.1 | Write requrements management plan |  |  |  |  | 2 devs | 1 | 2020-10-12 | 2020-10-12
1.2.4 | WBS | [5 empty] | 1
1.2.4.1 | Organize project management documents |  | 1.2.5.1 |  |  | 2 devs | 1 | 2020-10-19 | 2020-10-19 |  | s
1.2.4.2 | Decompose software components |  | 1.2.5.1 |  |  | 2 devs | 2 | 2020-10-19 | 2020-10-20
1.2.4.3 | Brainstorm other deliverables |  | 1.2.5.1 |  |  | 2 devs | 1 | 2020-10-20 | 2020-10-20
1.2.5 | WBS Dictionary | [5 empty] | 1
1.2.5.1 | Write descriptions of WBS items | 1.2.4.1, 1.2.4.2, 1.2.4.3 | 1.3.1.1 |  |  | 2 devs | 2 | 2020-10-21 | 2020-10-22
1.3.1 | Activity List and Attributes | [5 empty] | 1
1.3.1.1 | Breakdown WBS items into activities | 1.2.5.1 | 1.3.1.2 |  |  | 2 devs | 3 | 2020-10-26 | 2020-10-28
1.3.1.2 | Document activity attributes | 1.3.1.1 | 1.4.1.1, 1.4.2.1 |  |  | 2 devs | 2 | 2020-10-27 | 2020-10-28
1.3.2 | Milestone List | [5 empty] | 1
1.3.2.1 | Brainstorm project milestones |  |  |  |  | 2 devs | 1 | 2020-10-23 | 2020-10-23
1.4.1 | Cost Baseline | [5 empty] | 1
1.4.1.1 | Create cost baseline | 1.3.1.2 | 1.4.3.1 |  |  | 2 devs | 5 | 2020-10-29 | 2020-11-02
1.4.2 | Cost Estimate | [5 empty] | 1
1.4.2.1 | Calculate cost estimate | 1.3.1.2 |  |  |  | 2 devs | 2 | 2020-11-03 | 2020-11-04
1.4.3 | Earned Value Chart | [5 empty] | 1
1.4.3.1 | Create earned value chart | 1.4.1.1 |  |  |  | 2 devs | 2 | 2020-11-05 | 2020-11-06
1.5.1 | Quality Management Plan | [5 empty] | 1
1.5.1.1 | Write quality management plan |  |  |  |  | 2 devs | 1 | 2020-11-09 | 2020-11-09
1.5.2 | Quality Metrics | [5 empty] | 1
1.5.2.1 | Document quality metrics |  |  |  |  | 2 devs | 1 | 2020-11-09 | 2020-11-09
1.5.3 | Flow Chart | [5 empty] | 1
1.5.3.1 | Create flow chart of development pipeline |  |  |  |  | 2 devs | 1 | 2020-11-10 | 2020-11-10
1.6.1 | Staffing Management Plan | [5 empty] | 1
1.6.1.1 | Create staffing management plan |  |  |  |  | 2 devs | 1 | 2020-11-11 | 2020-11-11
1.6.1.2 | Create organizational chart |  |  |  |  | 2 devs | 1 | 2020-11-12 | 2020-11-12
1.6.2 | RACI Chart | [5 empty] | 1
1.6.2.1 | Create RACI chart | 2.1.1.4 |  |  |  | 2 devs | 1 | 2020-11-13 | 2020-11-13
2.1.1 | Software Requirments Specification | [5 empty] | 1
2.1.1.1 | Interview project sponsor |  | 2.1.1.4 |  |  | 2 devs | 1 | 2020-10-13 | 2020-10-13
2.1.1.2 | Interview drivers |  | 2.1.1.4 |  |  | 2 devs | 1 | 2020-10-14 | 2020-10-14
2.1.1.3 | Create use cases |  | 2.1.1.4 |  |  | 2 devs | 1 | 2020-10-15 | 2020-10-15
2.1.1.4 | Write software requirements specification | 2.1.1.1, 2.1.1.2, 2.1.1.3 | 1.6.2.1, 3.1.1.1 |  |  | 2 devs | 2 | 2020-10-15 | 2020-10-16
3.1.1 | Software Design Specification | [5 empty] | 1
3.1.1.1 | Write software design specification | 2.1.1.4 |  |  |  | 2 devs | 3 | 2020-11-17 | 2020-11-19
3.2.1 | Communication Management Plan | [5 empty] | 1
3.2.1.1 | Write communication management plan |  |  |  |  | 2 devs | 1 | 2020-11-16 | 2020-11-16
4.1.1 | ThirdParty Map License | [5 empty] | 1
4.1.1.1 | Research 3rd party map license |  | 4.1.1.2 |  |  | 1 devs | 1
4.1.1.2 | Purchase 3rd party map license | 4.1.1.1 |  |  |  | 1 devs | 1
4.2.1 | Login Screen | [5 empty] | 1
4.2.1.1 | Create login user interface |  | 4.2.1.2 |  |  | 1 devs | 2 | 2020-12-10 | 2020-12-11
4.2.1.2 | Create login control script | 4.2.1.1 |  |  |  | 1 devs | 2 | 2020-12-10 | 2020-12-11
4.2.2 | Map Screen | [5 empty] | 1
4.2.2.1 | Integrate 3rd party map |  | 4.2.3.1 |  |  | 1 devs | 1 | 2020-11-20 | 2020-11-20 | Planning processes complete
4.2.3 | Routing Module | [5 empty] | 1
4.2.3.1 | Create functions to controle routing | 4.2.2.1 |  |  |  | 1 devs | 5 | 2020-11-23 | 2020-11-27
4.2.4 | Delivery Details Screen | [5 empty] | 1
4.2.4.1 | Create delivery details user interface |  | 4.2.4.2 |  |  | 1 devs | 2 | 2020-11-30 | 2020-12-01
4.2.4.2 | Create delivery details control script | 4.2.4.1 |  |  |  | 1 devs | 2 | 2020-12-02 | 2020-12-03
4.2.4 | Server Interfcae Module | [5 empty] | 1
4.2.5.1 | Create script to call server API | 4.3.1.1 |  |  |  | 1 devs | 6 | 2020-12-04 | 2020-12-09
4.3.1 | App API Module | [5 empty] | 1
4.3.1.1 | Create script to control driver app API calls |  | 4.2.5.1 |  |  | 1 devs | 3 | 2020-11-24 | 2020-11-26
4.3.2 | External Subsystem API Module | [5 empty] | 1
4.3.2.1 | Create script to control subsystem API calls |  |  |  |  | 1 devs | 4 | 2020-11-27 | 2020-11-30
4.3.3 | Database Access Module | [5 empty] | 1
4.3.3.1 | Create module to access database |  | 4.5.1.2 |  |  | 1 devs | 1 | 2020-12-01 | 2020-12-01
4.4.1 | Development Database | [5 empty] | 1
4.4.1.1 | Set up development database |  | 4.4.2.1, 4.4.3.1 |  |  | 1 devs | 4 | 2020-11-20 | 2020-11-23 | Planning processes complete
4.4.2 | Driver Table | [5 empty] | 1
4.4.2.1 | Create driver table/cluster | 4.4.1.1 |  |  |  | 1 devs | 1 | 2020-11-23 | 2020-11-23
4.4.3 | Delivery Table | [5 empty] | 1
4.4.3.1 | Create delivery table/cluster | 4.4.1.1 |  |  |  | 1 devs | 1 | 2020-11-23 | 2020-11-23
4.5.1 | Login Page | [5 empty] | 1
4.5.1.1 | Create admin login page html & css |  |  |  |  | 1 devs | 4 | 2020-12-11 | 2020-12-14
4.5.1.2 | Write server-side script to verify login credentials | 4.3.3.1 |  |  |  | 1 devs | 4 | 2020-12-11 | 2020-12-14
4.5.2 | Dashboard | [5 empty] | 1
4.5.2.1 | Create dashboard page html & css |  |  |  |  | 1 devs | 1 | 2020-12-15 | 2020-12-15
4.5.3 | Add Driver Form | [5 empty] | 1
4.5.3.1 | Create add driver form html & css |  |  |  |  | 1 devs | 2 | 2020-12-07 | 2020-12-08
4.5.3.2 | Write js script to verify driver information |  |  |  |  | 1 devs | 3 | 2020-12-08 | 2020-12-10
4.5.4 | Edit Driver Form | [5 empty] | 1
4.5.4.1 | Create edit driver information form html & css |  |  |  |  | 1 devs | 3 | 2020-12-28 | 2020-12-30
4.5.4.2 | Write js script to verify driver information |  |  |  |  | 1 devs | 3 | 2020-12-28 | 2020-12-30
4.5.4.3 | Write script to display current driver info |  |  |  |  | 1 devs | 3 | 2020-12-28 | 2020-12-30
4.6.1 | Instruction Guide | [5 empty] | 1
4.6.1.1 | Write user manual |  |  |  |  | 2 devs | 1
5.1.1 | Server Integration Tests | [5 empty] | 1 |  |  | Server Modules Complete
5.1.1.1 | Create server integration tests |  |  |  |  | 1 devs | 3 | 2020-12-02 | 2020-12-04
5.1.1.2 | Perform server integration tests |  |  |  |  | 1 devs | 3 | 2020-12-02 | 2020-12-04
5.1.2 | App Integration Tests | [5 empty] | 1 |  |  | App Modules Complete
5.1.2.1 | Create server integration tests |  |  |  |  | 1 devs | 3 | 2020-12-14 | 2020-12-16
5.1.2.2 | Perform server integration tests |  |  |  |  | 1 devs | 3 | 2020-12-14 | 2020-12-16
5.1.3 | System Tests | [5 empty] | 1 |  |  | App and Server successfully integrated
5.1.3.1 | Create system tests |  |  |  |  | 2 devs | 2 | 2020-12-23 | 2020-12-24
5.1.3.2 | Perform system tests |  |  |  |  | 2 devs | 2 | 2020-12-23 | 2020-12-24
6.1.1 | Final Report | [5 empty] | 1
6.1.1.1 | Write final report |  |  |  |  | 2 devs | 1
6.1.1.2 | Create lessons learned document |  |  |  |  | 2 devs | 1
6.2.1 | Source Code | [5 empty] | 1
6.2.1.1 | Package source code |  |  |  |  | 2 devs | 3 | 2020-12-01 | 2020-12-03
6.2.2 | Deployed Server | [5 empty] | 1
6.2.2.1 | Deploy server |  |  |  |  | 1 devs | 5 | 2020-12-01 | 2020-12-05
6.2.2.2 | Record server information |  |  |  |  | 1 devs | 5 | 2020-12-01 | 2020-12-05
6.2.4.1 | Build final version of app |  |  |  |  | 1 devs | 5 | 2020-12-01 | 2020-12-05
6.3.1 | Navigation Devices | [5 empty] | 1
6.3.1.1 | Package naviagtion devices |  |  |  |  | 1 devs | 1