## Sheet1
Cost Baseline
Project Name: | Date:
Note: Enter your WBS and costs each month. Add/delete rows and columns as needed and check all formulas (bolded below).
| 1 | 2 | 3 | 4 | Total Cost
WBS Categories
1.0 Project Management
1.1 Integration Management | 1520 |  |  |  | 1520
1.2 Scope Management | 1540 |  |  |  | 1540
1.3 Schedule Management | 840 |  |  |  | 840
1.4 Cost Management | 360 | 840 |  |  | 1200
1.5 Quality Management |  | 580 |  |  | 580
1.6 Resource Management |  | 480 |  |  | 480
2.0 Product Requirements
2.1 Software | 1400 |  |  |  | 1400
3.0 Detail Design & Analysis
3.1 Software |  | 1400 |  |  | 1400
3.2 Stakeholder Communication |  | 500 |  |  | 500
4.0 Construct
4.1 Software Licensing |  | 400 |  |  | 400
4.2 App
4.2.1 Login Screen |  |  | 400 |  | 400
4.2.2 Map Screen |  | 200 |  |  | 200
4.2.3 Routing Module |  | 1000 |  |  | 1000
4.2.4 Delivery Details Screen |  | 200 | 600 |  | 800
4.2.5 Server Interface Module |  |  | 800 |  | 800
4.3 Server
4.3.1 App API Module |  | 600 |  |  | 600
4.3.2 External Subsystem API |  | 400 |  |  | 400
4.3.3 Database Access Module |  |  | 200 |  | 200
4.4 Database
4.4.1 Development Database |  | 600 |  |  | 600
4.4.2 Driver Table |  | 100 |  |  | 100
4.4.3 Delivery Table |  | 100 |  |  | 100
4.5 Administrator Access Website
4.5.1 Login Page |  |  | 800 |  | 800
4.5.2 Dashboard |  |  | 200 |  | 200
4.5.3 Add Driver Form |  |  | 800 |  | 800
4.5.4 Edit Driver Info Form |  |  | 800 |  | 800
4.6 User Documentation
4.6.1 Instruction Guide |  |  | 480 |  | 480
5.0 Integration and Test
5.1 Software |  |  | 2000 |  | 2000
6.0 Closing Process
6.1 Documents |  |  |  | 800 | 800
6.2 Software |  |  |  | 2100 | 2100
6.3 Hardware |  |  | 25000 | 300 | 28000
Reserves |  |  |  | 15312
Total | 5660 | 7400 | 32080 | 18512 | 63652
*Reserves are all entered in month 12