## Sheet1
Cost Estimate
Project Name: Routing Subsytem | Date:11/3/2020
WBS Categories | Internal Labor | $/hour | Internal $ Total | External Labor | $/hour | External $ Total | Total Labor | Non-labor $ | Total Cost
1.0 Project Management | 192
1.1 Integration Management | 44
1.1.1 Project Charter | 8 | 30 | 240 | 1 | 100 | 100 | 340 |  | 340
1.1.2 Project Management Plan | 16 | 30 | 480 | 1 | 100 | 100 | 580 |  | 580
1.1.3 Assumption Log | 4 | 30 | 120 | 0 |  | 0 | 120 |  | 120
1.1.4 Business Case | 16 | 30 | 480 | 0 |  | 0 | 480 |  | 480
1.2 Scope Management | 48
1.2.1 Scope Management Plan | 8 | 30 | 240 | 1 | 100 | 100 | 340 |  | 340
1.2.2 Scope Statement | 8 | 30 | 240 | 0 |  | 0 | 240 |  | 240
1.2.3 Requirements Management Plan | 8 | 30 | 240 | 0 |  | 0 | 240 |  | 240
1.2.4 Work Breakdown Structure (WBS) | 16 | 30 | 480 | 0 |  | 0 | 480 |  | 480
1.2.5 WBS Dictionary | 8 | 30 | 240 | 0 |  | 0 | 240 |  | 240
1.3 Schedule Management | 28
1.3.1 Activity List and Attributes | 24 | 30 | 720 | 0 |  | 0 | 720 |  | 720
1.3.2 Milestone List | 4 | 30 | 120 | 0 |  | 0 | 120 |  | 120
1.4 Cost Management | 40
1.4.1 Cost Baseline | 16 | 30 | 480 | 0 |  | 0 | 480 |  | 480
1.4.2 Cost Estimate | 16 | 30 | 480 | 0 |  | 0 | 480 |  | 480
1.4.3 Earned Value Chart | 8 | 30 | 240 |  |  | 0 | 240 |  | 240
1.5 Quality Management | 16
1.5.1 Quality Management Plan | 8 | 30 | 240 | 1 | 100 | 100 | 340 |  | 340
1.5.2 Quality Metrics | 4 | 30 | 120 | 0 |  | 0 | 120 |  | 120
1.5.3 Flow Chart | 4 | 30 | 120 | 0 |  | 0 | 120 |  | 120
1.6 Resource Management | 16
1.6.1 Staffing Management Plan | 8 | 30 | 240 | 1 |  | 0 | 240 |  | 240
1.6.2 RACI Chart | 8 | 30 | 240 | 0 |  | 0 | 240 |  | 240
2.0 Product Requirements | 24
2.1 Software | 24
2.1.1 Software Requirements Specification | 24 | 50 | 1200 | 2 | 100 | 200 | 1400 |  | 1400
3.0 Detail Design & Analysis | 32
3.1 Software | 24
3.1.1 Software Design Specification | 24 | 50 | 1200 | 2 | 100 | 200 | 1400 |  | 1400
3.2 Stakeholder Communication | 8
3.2.1 Communication Management Plan | 8 | 50 | 400 | 1 | 100 | 100 | 500 |  | 500
4.0 Construct | 164
4.1 Software Licensing | 8
4.1.1 Third Party Map License | 8 | 50 | 400 | 0 |  | 0 | 400 |  | 400
4.2 App | 64
4.2.1 Login Screen | 8 | 50 | 400 | 0 |  | 0 | 400 |  | 400
4.2.2 Map Screen | 4 | 50 | 200 | 0 |  | 0 | 200 |  | 200
4.2.3 Routing Module | 20 | 50 | 1000 | 0 |  | 0 | 1000 |  | 1000
4.2.4 Delivery Details Screen | 16 | 50 | 800 | 0 |  | 0 | 800 |  | 800
4.2.5 Server Interface Module | 16 | 50 | 800 | 0 |  | 0 | 800 |  | 800
4.3 Server | 24
4.3.1 App API Module | 12 | 50 | 600 | 0 |  | 0 | 600 |  | 600
4.3.2 External Subsystem API | 8 | 50 | 400 | 0 |  | 0 | 400 |  | 400
4.3.3 Database Access Module | 4 | 50 | 200 | 0 |  | 0 | 200 |  | 200
4.4 Database | 16
4.4.1 Development Database | 12 | 50 | 600 | 0 |  | 0 | 600 |  | 600
4.4.2 Driver Table | 2 | 50 | 100 | 0 |  | 0 | 100 |  | 100
4.4.3 Delivery Table | 2 | 50 | 100 | 0 |  | 0 | 100 |  | 100
4.5 Administrator Access Website | 52
4.5.1 Login Page | 16 | 50 | 800 | 0 |  | 0 | 800 |  | 800
4.5.2 Dashboard | 4 | 50 | 200 | 0 |  | 0 | 200 |  | 200
4.5.3 Add Driver Form | 16 | 50 | 800 | 0 |  | 0 | 800 |  | 800
4.5.4 Edit Driver Info Form | 16 | 50 | 800 | 0 |  | 0 | 800 |  | 800
4.6 User Documentation | 0
4.6.1 Instruction Guide | 0 | 50 | 0 | 8 | 60 | 480 | 480 |  | 480
5.0 Integration and Test | 40
5.1 Software | 40
5.1.1 Server Integration Tests | 12 | 50 | 600 | 0 |  | 0 | 600 |  | 600
5.1.2 App Integration Tests | 12 | 50 | 600 | 0 |  | 0 | 600 |  | 600
5.1.3 System Tests | 16 | 50 | 800 | 0 |  | 0 | 800 |  | 800
6.0 Closing Process | 58
6.1 Documents | 16
6.1.1 Final Report | 16 | 50 | 800 | 1 |  | 0 | 800 |  | 800
6.2 Software | 42
6.2.1 Source Code | 14 | 50 | 700 | 0 |  | 0 | 700 |  | 700
6.2.2 Deployed Server | 10 | 50 | 500 | 0 |  | 0 | 500 |  | 500
6.2.3 Deployed Database | 10 | 50 | 500 | 0 |  | 0 | 500 |  | 500
6.2.4 Packaged app | 8 | 50 | 400 | 0 |  | 0 | 400 |  | 400
6.3 Hardware | 0
6.3.1 Navigation Devices | 0 | 50 | 0 | 30 | 10 | 300 | 300 | 25000 | 25300
Total | 510 |  | 5520 | 49 |  | 1680 | 23340 | 25000 | 48340
Assumptions